## Slide 1: Operating Model Redesign for Hughes Group
Calderwood Partners LLC — July 13, 2008
A progress briefing for the client sponsor, prepared by the engagement team. The engagement commenced May 18, 2008 and is scoped to run about eight months; this briefing covers the opening phase of the work.

## Slide 2: Where the work stands
  We are in the opening phase: mapping how the organization runs today before proposing any change to it.
  The core processes are being traced end to end, with particular attention to where decisions are made and where they stall.
  First data requests are out to the client finance team, and the cost picture is being assembled behind the process map.

## Slide 3: What the baseline is beginning to show
  The documented process and the process as actually run differ in a few predictable places, and that gap is where most of the friction sits.
  Accountability for several core results is split across functions, so no single owner sees a result from end to end.
  A shared cost center currently masks how two support functions consume resources; we are working with finance to separate them.

## Slide 4: The questions the redesign has to answer
  Where should decision rights sit, so that the people accountable for a result also control it?
  Which activities belong together in the model, and which are grouped that way only by history?
  What can the organization operate for itself once we have gone, as against what looks good only on paper?

## Slide 5: Your account team
  Jason Torres, Principal, holds the relationship and owns what we deliver.
  Brenda Rodriguez, Senior Consultant, leads the analysis and the operating and cost picture.
  Linda Gallegos, Chief Financial Officer, is our sponsor on the client side and our point of contact.

## Slide 6: What happens next
  Close out the baseline and the cost picture over the coming weeks.
  Shape two or three candidate models and test each against the baseline for what it costs and what it changes.
  Return to you with the options and their trade-offs before any direction is fixed.