## Slide 1: Growth Strategy for Key Group
Calderwood Partners LLC — August 24, 2009
  A progress briefing for Steven Lowe, Vice President, Finance
  Engagement commenced July 4, 2009
  Prepared by the engagement team
  Brenda Rodriguez, Senior Consultant, and Daniel Leach, Research Associate

## Slide 2: The Question We Are Working
  Where Key Group's growth comes from over the next several years, and what it takes to capture it
  Read the current position: where the company earns today, by segment and by customer
  Size the markets the company serves and the near ones it does not
  Frame the growth options and rank them on return and on what the company can execute

## Slide 3: How We Are Working
  We start from your own segment numbers, not from a template
  Daniel Leach is sizing the market from published sources and your figures, alongside the current-state work
  Interviews with the four segment leads run through this phase
  Every figure we show ties back to one your finance team already recognizes

## Slide 4: What We Are Hearing So Far
  Growth in the two largest segments looks concentrated in a handful of accounts, not spread across the base
  The nearest adjacent segments are larger than the core, and more contested
  Geographic extension comes up repeatedly in the interviews, with no clear read yet on its cost
  These are early observations from three of four interviews, offered as observations and not yet as findings

## Slide 5: Where the Work Stands
  Current-position picture built to segment level; customer detail in hand for the largest segment
  Market sizing under way, roughly half complete
  Three of the four segment-lead interviews done
  No growth options are on the table yet, and none should be read into this briefing

## Slide 6: What Comes Next
  Close the last interview and finish the market sizing
  Frame three or four growth options, with their requirements and returns, for discussion and not for decision
  Bring the current-position read and the option set to the next working session
  Questions to Brenda Rodriguez; data questions to Daniel Leach