## Slide 1: Pension Valuation for Howard and Sons
Meridian Actuarial Advisors LLC — May 21, 2016
  Engagement start: April 17, 2016
  Prepared by Jennifer Vasquez, Consulting Actuary
  Purpose: measure the plan's funded position and the contribution for the year ahead
  For the Howard and Sons board and staff

## Slide 2: What the valuation covers
  We measure the actuarial accrued liability and the normal cost under the plan's funding method.
  We report the funded ratio and a recommended contribution for the coming year.
  We reconcile this year's results to the prior valuation, so any change is explained and not just stated.
  We document every assumption and every data source that stands behind the numbers.
  Where the data cannot answer a question, we say so rather than estimate around it.

## Slide 3: How the work is staffed
  David Sherman reconciles the census and documents the data we rely on.
  Jeffrey Ochoa builds the valuation model and ties each result back to the assumption that drives it.
  Jennifer Vasquez signs the opinion and owns the judgment calls.
  Elizabeth Horne is our point of contact for data and plan questions.
  We confirm decisions in writing, so no one is working from an old version.

## Slide 4: What you will receive
  A workbook of exhibits: the liabilities, the assets, and the resulting funded position.
  A report that interprets the exhibits and states our opinion plainly.
  A short summary the board can read without the detail behind it.
  The full set of assumptions and data sources, laid out for review.

## Slide 5: Where we are now
  The participant census is in and being reconciled to last year's file.
  The year-end asset statement and one plan-provision question are still open with your team.
  The assumptions are carried from the last study and will be reviewed before any results.
  No results yet; the work at this point is settling the inputs.

## Slide 6: Next steps
  Send the year-end asset statement.
  Confirm the disability provision, so the valuation matches the plan document.
  We finish the census reconciliation and load the reviewed assumptions.
  We bring preliminary results back to you before anything is treated as final.