To: Pricing Study team; cc Melissa Sexton, VP Finance, Johnson PLC

From: Jenna Wiley, Principal Consultant

Re: Kickoff, Pricing Study

The engagement is signed and work begins March 28, 2020. This one runs differently from our usual playbook: all interviews and working sessions are by video until further notice, and the data room is electronic only. Plan your weeks around that; it changes the interview cadence, not the analysis.

Workstreams and owners:

1. Price waterfall build: land the transaction extract, validate it against the ledger, build the waterfall by product family. Owner: Lisa Hernandez.

2. Discounting practice: interview sales leadership and the two regional managers, document approval reality versus policy. Owner: Jenna Wiley.

3. Price architecture: synthesize into recommended structure and sequencing. Owner: Jenna Wiley, with Chad reviewing before anything goes to the client.

Data hygiene matters double on a remote engagement: confirm every extract by email with Ms. Sexton's office, log the receipt date, and file the raw pull before you touch a copy.

Next steps: Lisa sends the data request Monday. I will schedule the first three video interviews. Weekly check-in stands; same rule as always, what changed and what it costs, one page.