## Slide 1: Patent Portfolio Review: Odonnell Inc
Hollowell Patent Group PLLC — July 5, 2019
  Status briefing for Gary Smith, General Manager.
  Review under way since May 13, 2019.
  Prepared by Kelly Snyder, Patent Agent.
  Privileged and confidential. Attorney-client communication.

## Slide 2: Where the Work Stands
  Docket reconciled against patent office records. Your records and theirs agree on every open deadline.
  Maintenance fee on the older patent paid on your instruction. That patent stays in the review like any other.
  Earliest-filed families reviewed. Pending applications are next.
  Title review under way. Current product list received; claim mapping started.

## Slide 3: How Each Family Is Assessed
  Legal status and remaining term.
  Maintenance fees and annuities due through end of term.
  Chain of title as recorded, checked against the inventor agreements.
  Claim coverage of current and planned products.
  One recommendation per family: maintain, continue, or let lapse.

## Slide 4: Early Observations
  Older issued families are largely in order.
  Some may not justify their next maintenance payment. No recommendation yet.
  Recorded inventor assignments are incomplete on some older families.
  Most title gaps look curable by corrective assignment. That depends on the inventor agreements.
  All observations are provisional until Heather Munoz signs off.

## Slide 5: Team
  Heather Munoz, Partner. Supervises the review and signs the final report.
  Kelly Snyder, Patent Agent. Day-to-day contact; prosecution histories and claims.
  Amanda Schwartz, Associate. Chain of title and product mapping.

## Slide 6: What We Need in July
  Gary Smith: planned releases for the next two years.
  Gary Smith: the name of the officer who signs corrective assignments for the company.
  Amanda Schwartz: draft corrective assignments for your review.
  Kelly Snyder: finish the pending application families.
  Working session on interim findings, to be scheduled with your office.