## Slide 1: Transaction Readiness Review: Nguyen, Reynolds and Martinez
Fernhollow Partners LLC — July 18, 2022
Midpoint client briefing prepared for Nguyen, Reynolds and Martinez by Fernhollow Partners LLC. Presented by Sandra Perez, Director.

## Slide 2: Engagement Snapshot
  Readiness review under way since May 28, 2022
  Scope: data room build, quality of numbers, diligence preparation
  Client lead: Amanda Golden, VP Finance
  Seven-month program, now past its midpoint

## Slide 3: Progress Since Kickoff
  Data room index complete; core document batches loaded (Ryan Strong)
  Quality-of-numbers review through the annual statements (Briana Dennis)
  Remediation log established, ranked by importance, and shrinking
  No finding to date that would move a buyer's view of the numbers

## Slide 4: Open Items
  Remaining lease and contract schedules from the finance team
  Management diligence-question sessions to be scheduled
  Final pass on customer and supplier documentation

## Slide 5: Next Steps
  Close remaining remediation items with Amanda Golden's team
  Run the management preparation sessions
  Deliver the written readiness assessment
  Confirm timing for the closing board briefing