# Status Report: Valuation Analysis for Woods LLC

Prepared by Sandra Perez, Director, Fernhollow Partners LLC, for the Woods LLC executive team.

## Status Summary

The engagement is on schedule. What changed this period: the draft valuation model cleared second internal review, and the last open data item on the Woods LLC side was resolved and traced to source. What it means: the analytical work is substantially complete, and the remaining effort is drafting, review, and the board readout. What we need from you appears under Upcoming Work.

## Accomplishments This Period

Draft valuation model completed and through second internal review, with income and market approaches reconciled

Briana Dennis completed the draft report structure and the expanded market-approach appendix requested for the board

Ryan Strong finished the comparable-company tie-out; every figure in the model now traces to source

Final open client data item resolved with your controller's office

## Upcoming Work

Full draft report to you for factual review

Final partner review of the model and report before board materials are produced

Board readout deck prepared once factual-review comments are in

Confirmation of the board presentation window

## Budget

The engagement remains within the fixed fee of $83,500 set in the engagement letter. No scope changes have been requested or made, and we do not expect any adjustment. Invoicing continues on the monthly schedule.

## Risks

Board calendar: if the presentation window moves, the factual-review period compresses; early confirmation protects the schedule

Late data changes: any restatement of the monthly figures after factual review would require rework of the tie-out

Availability: the review period overlaps client close activities, so we have kept the factual-review packet deliberately short