To: Commissioning team; cc Lisa Brown, Chief Operating Officer, Vazquez, Sanchez and Gutierrez

From: Jeff Fowler, Engineering Manager

Re: Kickoff, Controls Retrofit Commissioning

Commissioning starts May 25, 2023. The contractor's checkout is reportedly ninety percent complete, which historically means seventy. Plan test days accordingly.

Assignments:

1. Functional performance tests and the issues log: John Johnson owns both. Every issue gets a number, a location, and a retest date; the log is the single source of truth with the contractor.

2. Test scripts: John drafts from the sequences of operations, Jeff reviews before anything is executed with the contractor watching.

3. Trend review: two-week post-acceptance trends land in the engagement folder weekly; flag anything that hunts, short-cycles, or never reaches setpoint.

Ground rules with the contractor: professional, specific, in writing. We fail tests, not people. Ms. Brown's office gets the issues log summary every Friday; no surprises in the monthly status report.

Next steps: John requests the points list and submittals today. First sampled point-to-point checkout is scheduled once the contractor confirms panel completion in writing.